# Essential SAFe - Dean Leffingwell
# Premise
Essential SAFe Milwaukee Scaling Agile Meetup Sponsored by Icon At Northwestern Mutual
# Presenter
Dean Leffingwell
# Attendees
Looked like 300 people in the room, friendly audience
# Reference
Dean Leffingwell - Essential SAFe
# Notes
Local “Cow” story Did visual. When there was a major impediment they put cow a visual cow on a visual track so that it was visible
Leffingwell's history Learn and like agile Started with XP Had failed implementation when started to get more people involved “Can do it 50 people but what about 2000”
Seeing SAFe implementations but some are not successful Question is what are the things that don't make work Some things we've seen include:
- No Inspect and adapt
- No planning and innovation iteration
- Individual art teams not themselves cross functional
- No system Demos
Also hearing
- SAFe is flexible - but we don't use arts
- … didn't include the teams training as “Our teams don't have time for training”
- and so on
“This shouldn't be funny”
Sometimes when Dean says things that aren't comfortable to organization he doesn't get invited back Says it's “a form of WIP limit” for him
But leads to the question “What is essential about SAFe?” Also leads to simplification / more incremental approach if that makes sense Single agile release train
And “Less of eye chart” Doesn't discount Big Picture but that is not appropriate for all
10 essentials of SAFe are:
1. Lean agile principles
2. Agile teams and trains
3. Cadence and sync
4. Critical team and program roles
5. PI planning
6. System demo
7. Inspect and adapt
8. PI iteration
9. Arch runway
10. Lean agile leaders
Rest of notes go through some of these
## Lean agile principles
Originally developed as a result of discussion from large scale system engineering. Response to “sure it works for IT / software but what about our stuff for a Satellite system”
On transformation in general we see “Pace of learning is fast; pace of adoption is slow” and we need to be careful about changing SAFe too much
If you are doing an exec presentation, concentrate of the principles as this explains SAFe without much else
Question - “do you see batch sizes; do you see queues” Answer is yes, you now see batch size; queues We know have conversation about WIP These are all changes as a result of how we think about things
If you find a practice isn't working for you, stop here first (i.e. principles), figure out which principles apply and work the issue that way
Book - DevOps handbook - Gene Kim / Jez Humble (new) - https://www.amazon.com/gp/product/B01M9ASFQ3?storeType=ebooks Talks about the same kinds of principles. First half of the book is about the stream of work.
## Agile teams and release trains
Idea behind teams and release trains is that if you do it (and based on value streams) you will Invert Conways law (software reflects organizational structure)
Without teams and trains
- Teams are isolated
- Lack of collaboration
- There is over specialization
- Not aligned
- Release late, Big Bang
- No arch / ux integrity
- Too much WIP, multiplexing, low productivity
The set up allows for “Resource pool” (people as resource, this is a lean concept even though we don't like calling people resources) The excess capacity allows work to flow through the system
Concept of centralized and decentralized decision making Idea that some centralized decisions makes sense But also note that concept of central vs decentral is dependent on point of view At my level we might have a central decision process, but if you move up a level, that same decision making process could be decentralized
## Cadence and synchronization
Benefits of Cadence
- Transforms unpredictable
- Makes wait times predictable
- Facilitate planning, provide more efficient use of resource
Benefits of Synchronization
- Causes multiple events to happen in the same way
- Sync events facilitate cross functional trade offs of people and scope
Discussion of sprint Sprint is scientific method / plan-do-check-act cycle Program increment is same at higher level
Idea is to apply Scientific method / plan-do-check-act at all levels Scientific method - https://en.wikipedia.org/wiki/Scientific_method?wprov=sfsi1
Idea - have you noticed that teams flex to the work of the ART Perhaps you started with a core technology (component) team, but then found that team did not have any work in the PI Those team members perhaps joined other (feature) teams If we suddenly found we have new work on the core technology area, do we reform the core team? Typically not - we just send the work to one of the teams Result is that team structure is more fluid
Without cadence and synchronization you will find
- Entropy increases
- Get the right people to meeting is impossible
- Integration comes late
- Tendency is to try and shove everything in current timebox
- No forced integration and evaluation people
- Teams are agile, but system not iterating
Discussion on entropy increasing unless you do something - The second law of thermodynamics states that the total entropy of an isolated system always increases over time (https://en.m.wikipedia.org/wiki/Second_law_of_thermodynamics) Planning event is a singulatory Note that you will start getting Entropy immediately after planning The next planning event brings it back together again
Example was 400 people that had a combined velocity of 0 Problem was that while everyone was saying they were working on the work, in reality everyone was working on something else
## Critical Team and train roles
Team roles
- Product owner needs to say “no” (add to list of things we want)
- Scrum master means you have discipline
- Team gets things done
Plus Train roles
- RTE
- Product management
- System arch/engineer
- Customer
- Business owner
Without roles
- Responsibly not clear
- Meeting waste of time not clear outcomes
- Teams find hard to integrate
- … (and others)
## PI planning
This is the magic It is far more than just a planning event - synchronization, alignment, common understanding, etc
Quote - “PowerPoint animation should be a controlled substance in our company”
Without PI planning
- Teams cannot come together
- “Building software is problem of building a social framework, with people that that aren't social”
So planning helps develop that social network.
## System demo
If you don't have a system demo
- You risk waterfall-Ing the PI
- You impact trust - no trust
- Business unclear of results
- There is no forcing function for ci and test automation
- You have individual system behaviors, but your train is not agile
Goal is to have system sprint, not just teams “Show me the system”
## Inspect and adapt
A lot of people say this event costs too much and you can't capitalize What proportion of the PI is the I&A - 0.7% The question you have to ask yourself is “why can't we afford to spend 0.7% of time fixing the stuff that lowers our velocity?”
Problem is that if you do not allocate time to do this you won't do it as there is too much pressure to get the next feature
Without the I&A
- Can't improve systemically
- Improvement effort address symptoms not root clauses
- Centralized improvements do reflect reality
Eventually, if this continues, since you are not showing improvement, management will tell you what to do to improve because you are not improving. And it won't be effective as they are too far away from the work
## IP iteration
Statement - “Agile not optimized for free association; Agile is optimized for value delivered”
If you have to deliver every sprint there is no time to innovate
So we need to provide capacity for innovation
Without the IP iteration
- No capacity to innovate so it doesn't happen
- No innovate as delivery option
## Arch runway
False velocity Arch deteriorates under pressure of now Solution robust reduces over time
## Lean agile leaders
Successful transform are based on education management first. They become lean thinking manager - teachers who lead rather than follow the transformation
Concept is that senior management have nice cushy floor with middle management, while the teams have a ceiling beyond which they cannot get the changes they need to become more effective. This means Managers (middle) has to be lean agile leaders - helping both sides, leading, teachers etc.
## Additional
In the process of creating SAFe implementation roadmap, beyond the 1-2-3 - coming soon
They are also in the process of developing an RTE course Expect to the hardest course, harder even than SPC, with harder test to qualify They will run a first alpha version in January
Concept Development value stream and operational value stream
On of the key values of safe is that it provides a common taxonomy which improves our ability to communicate Common taxonomy is needed for social network
~~LINKBACK~~ ~~DISCUSSION~~