# Johanna Rothman - Agile Program Management
# Premise
Do you have measurement dysfunction on your program? Are you trying to measure teams and extrapolate each team’s status to the program? That doesn’t work. Teams have personal status, and you can’t add them together to understand the program state. You can use a handful of program measurements that help everyone understand where the program is and where it’s headed.
Instead of trying to “scale” measurements, take a new approach. In this talk, Johanna will share program measurements—qualitative and quantitative—that show everyone the program state.
# Summary
- Content rating (0-no new ideas, 5 - a new ideas/approach, 9-new ideas): 5
- Style rating (0-average presentstion, 5 - my level, 9-I learned something about presenting): 3
# Action / Learning
- Quote - “People ask for predictive measures when they don't trust you to deliver” Johanna Rothman
- Book “This is lean”
- Write about this Individual Pay performance - “We are nuts” - Arguing about $500 or $1000 for a person that is paid $100K - In the rounding error
- Idea of action items as a Kanban board (measure - speed of decisions)
# Presentation
Original: https://submissions.agilealliance.org/attachments/2569
My copy: alpm.measurestoseevalueanddelivery.r1.pdf
# Note
Measurement problems with in programs
Program - several projects / one business objective
Several structures depending on structure of program
“People ask for predictive measures when they don't trust you to deliver” Because cannot depend on stream of value
Managers care about Customer acquisition / retention Revenue Customer experience
Change conversations for managers How much cost → how much invest (target date or budget) Are you on track, what the earned value → show working product When will we see revenue → show you value now / release now (when you send the bills out) What do the customers think → progress against release criteria, customer sat data
Story point / velocity “Do you want story point or do you want working software” - courageous team Measure of capacity, not productivity Not always predictable Individual to team
Team velocity is personal to team Team have different cycle time and lead times because they do different work We don't normalize stories inside or across teams
Can we measure learning Software is learning, innovation - maybe we have enough now We learn to build momentum
Hardware not done until in physical form
We need to learn to build momentum Earlier everyone can see something releasable, the more you build momentum
Use trend data, not snapshot data
Measure what you want to see and where you want to go First get to running testing features over time
Not traffic light management Until you see something. It's yellow They are for cars not programs
Measure completed, remaining and total features over time Including adding features Measure as a count Depends on deliverables, not epics or themes
Epics and themes - We can wave the hand, I can wave this way to
Product backlog burn up Feature set, stacked on top of one another. How much per unit time, show features grow, done as count Where are we up to

Can be done with stickies - one per feature Total and how much done
Added features for free Drive further metaphor - don't get the same release data
What would it take to release every day At least release every month
Agile roadmap in the large 6 quarter roadmap
Then agile roadmap in the small One quarter agile roadmap Deliverable based planning - small slices through the architecture Specific value for different users Rolling wave plan as not sure
How far out can we plan
Want less of WIP - CFD Defects Other less of - multi-tasking
How many projects are you working on - add sticky to wall once a week with number of projects
People respond to what you measure Measure what you want more of and less of Tell people which is which
Spike not WIP as it is learning
Program measurements Run rate / week and month - check against the target or investment question Program level WIP as feedback for program - product owner value team, feature teams momentum
Product owner value team Product manager Plus product owners - the deliverables
Release frequency
External release as a business decision Internal release - can you use continuous delivery inside your org If not how often can we release
Measure How long does it take to move from build to release Build time and is it increasing or decreasing
Cycle time (interdependencies show up here) - how long take a feature get in into release column If not feature teams then cycle time could be long
Product measures Create scenarios for what is important for your product Performance, reliability, quality attributes of the product Can be used as a release criteria
Qualitative measurements Customer feedback / happiness How often you get feedback from customers Obstacle report How long it takes to make a decision
Obstacle report

Decision times Kanban board for action items

Measurement traps Never attempt to measure anyone or any teams productivity (meaningless)
What is productivity? Features over time Teams take features not individual
Personal productivity is relevant because we
Resource efficiency is based on experts not flow
What flow efficient
Throughput
Book “this is lean”
Want flow efficiency Increase throughput Decrease WIP
Cost or date question
Do you want resilience or prediction?

If you must estimate 3 point estimate Swag Add percentage confidence
15% in April, 30% in May
And give a date for the next estimate
Deliver often to build trust Maybe release early
Individual Pay performance “We are nuts” Arguing about $500 or $1000 for a person that is paid $100K In the rounding error
Your are a team - hear is a pot of money for the team
~~LINKBACK~~ ~~DISCUSSION~~